## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Choose tablet vendor
Number of tablets | Calculate the number of tablets needed for both locations | 1.1667 | 1 | 1 | 2
Research tablet vendors | Research various tablet vendors and shortlist a few | 1.1667 | 1 | 1 | 2
Get quotes from vendors | Ask for quotes from the shortlisted vendors and compare costs | 1.1667 | 1 | 1 | 2
Select a tablet vendor |  | 1.1667 | 1 | 1 | 2
Choose an upgrade plan for tablets | In case of tablet breakage, choose an upgrade plan for tablets with vendor | 1.1667 | 1 | 1 | 2
Create contracts and SOW for vendor |  | 1.1667 | 1 | 1 | 2
Sign contract with tablet vendor |  | 1.1667 | 1 | 1 | 2
Milestone: Order and Shipment
Order tablets | Place order through Seydou | 1.1667 | 1 | 1 | 2
Recieve order shipment |  | 7 | 4 | 7 | 10 | H
Distribute and ship the tablets | Divide the shipment and distribute to North and Downtown locations | 1.1667 | 1 | 1 | 2
Milestone: Purchase accessories for tablets
Find vendors for protective cases and stands for tablets |  | 1.1667 | 1 | 1 | 2
Comapre costs between vendors and select a vendor |  | 1.1667 | 1 | 1 | 2
Place orders for accessories |  | 0.83333 | 1 | 1 | 0
Recieve order |  | 5.1667 | 3 | 5 | 8
Milestone: Installation and integration of tablet
Schedule an electrician for Downtown | Check with electrician if mornings or evenings work better | 2 | 2 | 2 | 2 | M
Schedule electrician for North | Notify GMs when to close their location | 2 | 2 | 2 | 2 | M
Install tablets at the bar areas in Downtown location |  | 2 | 1 | 2 | 3
Install tablets at the bar areas in North locations |  | 2 | 1 | 2 | 3
Upgrade POS system in both locations | If Sauce and Spoon is using a lower version | 2.6667 | 0 | 3 | 4 | L
Integrate the tablet software with the host and POS software in Downtown |  | 1 | 0 | 1 | 2 | L
Integrate the tablet software with the host and POS software in North |  | 1 | 0 | 1 | 2 | L
Test the basic working of the tablets insatlled |  | 1.1667 | 1 | 1 | 2
Milestone: Update the menu on tablet
Connect the Sauce and Spoon marketing team with the chosen tablet team for branding |  | 1.1667 | 1 | 1 | 2
Recieve menu and coupon values | From Carter | 7.8333 | 5 | 7 | 14 | M
Send content to designer |  | 1.1667 | 1 | 1 | 2
Design the tablet menu outlook - feasible mockups |  | 5.5 | 3 | 5 | 10
Select a final tablet menu outlook |  | 1.1667 | 1 | 1 | 2
Upload the design |  | 1 | 0 | 1 | 2 | H
Milestone: End-to end test run
Test end-to-end working of the tablet in Downtown | Ordering, recieving the order, generating the bill, transfer of money | 1.1667 | 1 | 1 | 2
Test end-to-end working of the tablet in North | Ordering, recieving the order, generating the bill, transfer of money | 1.1667 | 1 | 1 | 2
Milstone: Training
Pre training Downtown | Introduce tablets and changes to staff before training | 1.1667 | 1 | 1 | 2 | H
Pre training North | Introduce tablets and changes to staff before training | 1.1667 | 1 | 1 | 2 | H
Schedule tablet training session for the GMs and KMs of both the locations | GMs and KMs of both locations will be trained together | 1.1667 | 1 | 1 | 2 | H
Develop a training program for the FOH and BOH staff |  | 5.6667 | 4 | 5 | 10 | H
Schedule tablet training sessions for the staff of North location lead by GM |  | 1 | 1 | 1 | 1 | L
Schedule tablet training session for the staff of Downtown location lead by GM |  | 1.1667 | 1 | 1 | 2 | L
Milstone: Launch day
Create a launch day plan: staffing, troubleshooting, etc |  | 2 | 1 | 2 | 3
Invite all stakeholders and employees involved for launch day |  | 1.1667 | 1 | 1 | 2
Launch the tablets in Downtown |  | 1.1667 | 1 | 1 | 2
Launch the tablets in North |  | 1.1667 | 1 | 1 | 2
Milestone: Test run with public
Invite friends and family for the test run of the tablets |  | 1.1667 | 1 | 1 | 2
Implement a post dining survey to access customer satisfaction |  | 1 | 1 | 1 | 1

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Best Uses for Tablets at your Restaurants | https://www.business.com/articles/best-tablet-uses-restaurants/ | 2023-05-03 | Tablets should be paired with card readers, Also inquire about stands, protective cases and styluses for tablet.
Tablets in Restaurants: 3 Things You Need to Consider | https://nextrestaurants.com/point-of-sale/tablets-in-restaurants-what-you-need-to-consider/ | 2023-05-03 | Tablets will break/stop working. etc. Choose an upgrade plan with the tablet provider

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer satisfaction - faster, more efficient experience | Amt of time between placing an order and delivering it to the table - for appetizers is 8 mins | For a given appetizer order, how long is it taking to deliver the order to the table once the ticket is raised? | Measure the average time taken between recieving the appetizer order and the time the order is served to the table | FALSE
Customer satisfaction - faster, more efficient experience | Amt of time between placing an order and delivering it to the table - for entrees is 12-15 mins | For a givenentree order, how long is it taking to deliover the order to the table once the ticket is raised? | Measure the average time taken between recieving the entree order and the time the order is served to the table | FALSE
Customer satisfaction - faster, more efficient experience | Reduce average table turn time by 30 mins | How long was table turn time before the implementation of tablets and how long is the table turn time after tablet rollout? | Measure the average table turn time | FALSE
Customer satisfaction - faster, more efficient experience | Checkout time of 1 min or less | What is the level of ease during checkout? Are the customers running into problems during checkout? Do they need external help for checkout? | Measure the time elapsed from the time customer hits checkout to the end of the process. Measure the frequency of external help during checkout. | FALSE
Customer satisfaction - faster, more efficient experience | Less than 5% of customers who use the tablets to report technical issues each week | Are the customers satisfied with the dining experience? | Measure the percentage of customers asking for external help during the ordering process | FALSE
Customer satisfaction - faster, more efficient experience | 98% order accuracy | Are the customers sending back the delivered food back to the kitchen? | Measure the percentage of orders returned to the kitchen due to inaccurate order | FALSE
Customer satisfaction - faster, more efficient experience | Average wait time of 10 mins or less before customers are seated | How long are the cutomers waiting before they are seated? Are customers rexiting due to long wait time? | Measure the time between the customers entry to the restaurant and the time they are seated at a table. | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Amt of time between placing an order and delivering it to the table - for appetizers is 8 mins | For a given appetizer order, how long is it taking to deliver the order to the table once the ticket is raised? | Measure the average time taken between recieving the appetizer order and the time the order is served to the table | Were you satisfied with the service after ordering? | Yes/No | Yes | No
Amt of time between placing an order and delivering it to the table - for appetizers is 8 mins | For a given appetizer order, how long is it taking to deliver the order to the table once the ticket is raised? | Measure the average time taken between recieving the appetizer order and the time the order is served to the table | How long did you wait to recieve the appetizers after ordering? | Multiple choice | 5-10 mins | 10-15 min | <15mins
Amt of time between placing an order and delivering it to the table - for entrees is 12-15 mins | For a givenentree order, how long is it taking to deliover the order to the table once the ticket is raised? | Measure the average time taken between recieving the entree order and the time the order is served to the table | Were you satisfied with the service after ordering? | Yes/No | Yes | No
Amt of time between placing an order and delivering it to the table - for entrees is 12-15 mins | For a givenentree order, how long is it taking to deliover the order to the table once the ticket is raised? | Measure the average time taken between recieving the entree order and the time the order is served to the table | How long did you wait to recieve the entree after ordering? | Multiple choice | 5-10 mins | 10-15 min | <15mins
Reduce average table turn time by 30 mins | How long was table turn time before the implementation of tablets and how long is the table turn time after tablet rollout? | Measure the average table turn time | Has your productivity increased in terms of clearing the table and seating the next customer? | Yes/No | Yes | No
Reduce average table turn time by 30 mins | How long was table turn time before the implementation of tablets and how long is the table turn time after tablet rollout? | Measure the average table turn time | How long does it take to clear a table and seat the next customer? | Multiple choice | 1-2 mins | 2-3 mins | <5 mins
Checkout time of 1 min or less | What is the level of ease during checkout? Are the customers running into problems during checkout? Do they need external help for checkout? | Measure the time elapsed from the time customer hits checkout to the end of the process. Measure the frequency of external help during checkout. | How long did it take you to complete the checkout process today? | Multiple choice | 1-2 mins | 2-3 mins | <5mins
Checkout time of 1 min or less | What is the level of ease during checkout? Are the customers running into problems during checkout? Do they need external help for checkout? | Measure the time elapsed from the time customer hits checkout to the end of the process. Measure the frequency of external help during checkout. | How satisfied are you using the tablet to checkout? | Yes/No | Yes | No
Less than 5% of customers who use the tablets to report technical issues each week | Are the customers satisfied with the dining experience? | Measure the percentage of customers asking for external help during the ordering process | On a scale of 1-5 with 1 being the lowest and 5 the highest how easy was it to use the tablet? | Scaled | 1 | 2 | 3 | 4 | 5
Less than 5% of customers who use the tablets to report technical issues each week | Are the customers satisfied with the dining experience? | Measure the percentage of customers asking for external help during the ordering process | Did you come across any technical glitch while using the tablet? | Yes/No | Yes | No
98% order accuracy | Are the customers sending back the delivered food back to the kitchen? | Measure the percentage of orders returned to the kitchen due to inaccurate order | Was the food perpared as per your order today? | Yes/No | Yes | No
98% order accuracy | Are the customers sending back the delivered food back to the kitchen? | Measure the percentage of orders returned to the kitchen due to inaccurate order | If no for the above question, please elaborate | Open-ended
Average wait time of 10 mins or less before customers are seated | How long are the cutomers waiting before they are seated? Are customers rexiting due to long wait time? | Measure the time between the customers entry to the restaurant and the time they are seated at a table. | How long did you have to wait before being seated today? | Multiple choice | 0-5 mins | 5-10 mins | <10 mins
Average wait time of 10 mins or less before customers are seated | How long are the cutomers waiting before they are seated? Are customers rexiting due to long wait time? | Measure the time between the customers entry to the restaurant and the time they are seated at a table. | Were you satisfied with your wait time today? | Yes/No | Yes | No