## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | 40% of guests rated their experience as a 4 out of 5 | Data point from the survey | Continue to monitor customer ratings and work to improve the overall satisfaction
Customers | Went well | 78% of the customers signed up for the newsletter on the tablets | Data point from the survey | Analyze data to identify any trends or patterns associated with customer satisfaction. Send welcome email for all signed up customers.
Customers | Went well | 82% of the customers found the checkout process quick, easy and secure | Data point from the survey | Address technical glitches during checkout. Have an alternate check out process ready for cash payment.
Customers | Needs improvement | 54% of the customers waited 15+ mins for the table | Data point from the survey | Give a comprehensive training to both BOH and FOH so they understand each others work better
Customers | Needs improvement | 56% of the customers waited ~20 mins to recieve their order | Data point from the survey | Hire more kitchen staff to satisfy the increase in orders volume
Customers | Needs improvement | 28% of the customers stated their order was prepared incorrectly | Data point from the survey | Train the kitchen satff on reading the orders and double checking before serving - kitchen opertaions training
Project team | Went well | All the tablets were installed and working in both the locations | Quoted by Alex and confirmed by Gilly | Fix the technical glitches encountered and monitor for updates and manitence
Project team | Went well | All the guests got the hang of the tablets and payments worked for most part | Quoted by Gilly | Waiters should be alert to help customers if needed
Project team | Went well | Tickets came through at a good pace and were easy to keep track of | Quoted by Zane | Continue to monitor and track tickets
Project team | Needs improvement | Some amount of orders got sent back | Quoted by Zane and confirmed by Larissa | Prioritize this issue for further analysis. Schedule meeting with Larissa to understand kitchen operations updates
Project team | Needs improvement | Did not get many participants for birthday club | Quoted by Seyduo | Find ways to grow the list. Work with designer to display a clear content about the birthday club program
Project team | Needs improvement | During tablet implementation and training encountered internal operational issues that werent accounted for. | Quoted by Peta | For next rollout understand each locations history before planning